## README
MetLife Japan ¦ Golden Application Inventory — archetype classification
The single reference every domain team classifies against. One rule set, applied identically to all 142 applications.
WHAT THIS IS
| Purpose | The authoritative archetype classification for all 142 applications in Appendix 3 v2. Every domain model must classify against this sheet rather than re-deriving its own.
| Why it exists | The archetype sets three ceilings and one method for every application — the AI ceiling, the offshore ceiling, the transition mechanic and the sourcing construct. If two domains classify the same way differently, their prices are not comparable.
| It is live, not a snapshot | The archetype column is a formula, not a value. Change a source field and the classification, the parameters and both summaries re-derive.
HOW TO USE IT — FOR A DOMAIN TEAM
| 1 · Filter | Open Golden Inventory and filter column E to your 領域. The sheet has an autofilter on row 4.
| 2 · Read your mix | Go to Domain Summary and find your row. It gives your application count, effort, archetype mix and the weighted AI and offshore ceilings for your domain. Those are the starting parameters for your model.
| 3 · Cut your value streams | Group your applications into functional value streams. Reconcile to your domain effort exactly before you build any pod.
| 4 · Do not re-derive the archetype | If you believe an application is misclassified, use the Override column and record who and why. Do not change the rule.
THE RULE, IN ORDER
| Rule 1 → D | Primary code language contains COBOL, Assembler, ASM, RPG, EASYPLUS or PL/I. Mainframe and AS/400 estate.
| Rule 2 → C | Not rule 1, and Priority Transfer Targets = Y. The ten applications MetLife has already flagged for transfer.
| Rule 3 → B | Not rules 1 or 2, and Cloud Indicator = Yes. Cloud-migrated, so re-platformed, documented and specifiable.
| Rule 4 → A | Everything else. On-premises, non-mainframe, not flagged for transfer — where Japanese business context is bound to the application.
| Order matters | The rules are exclusive and evaluated top to bottom. An application matching more than one test takes the first.
RECONCILIATION AGAINST SECTION 4.1
| Application counts | Match exactly for all four archetypes: A 71, B 33, C 10, D 28.
| Effort | B and C match exactly (379.5 and 569.9). A and D differ by 4.7 units in opposite directions — this sheet gives A 317.1 and D 237.5 against Section 4.1's A 321.8 and D 232.8.
| Which to use | This sheet. The figures here are reproducible from the source fields; the Section 4.1 A/D split is not. Section 4.1 should be corrected to match.
GOVERNANCE
| Owner | Solution architecture. Changes to the rule require agreement across all eleven domain teams, because the rule sets the price.
| Overrides | Permitted, but only on the Overrides sheet with a named owner, a date and a reason. An override changes one application, never the rule.
| Source | Appendix 3 v2 — "03 [Appendix 3] Target EA Inventory v2.xlsx", sheet ApplicationList. 142 applications, 1,504.0 effort units.
| Known data gap | Named supply (FTC + FTE + MGCC) sums to 1,458.8 against 1,504.0 of effort. The 45.2-unit gap sits in 15 applications, mostly Storage & Preservation and Data Infrastructure. Raised as a clarification; not allocated here.

## Classification Rules
Classification rules and the parameters each archetype carries
Blue cells are inputs. The Golden Inventory reads every parameter from this sheet, so changing it here changes it everywhere.
A. THE RULE — evaluated in order, first match wins
| Rule | Archetype | Name | Test applied to the source field | Apps | Effort
| Rule 1 | D | Legacy-coupled core | Primary code language contains COBOL, Assembler, ASM, RPG, EASYPLUS or PL/I | 28 | 237.5078
| Rule 2 | C | MGCC-destined | Not rule 1, and Priority Transfer Targets = Y | 10 | 569.8803
| Rule 3 | B | Offshore-ready | Not rules 1-2, and Cloud Indicator = Yes | 33 | 379.5045
| Rule 4 | A | Language-locked | Everything else — on premises, not mainframe, not a transfer target | 71 | 317.0835
|  |  | Total |  | 142 | 1503.976
B. WHY EACH ARCHETYPE IS ITS OWN GROUP
| D | Legacy-coupled core | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation.
| C | MGCC-destined | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice.
| B | Offshore-ready | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate.
| A | Language-locked | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads.
C. AI CEILING — phase effort mix x AI-addressable share per phase
| Delivery phase | Share of effort | A | B | C | D
| Requirements & impact analysis | 15% | 22% | 35% | 35% | 35%
| Design & architecture | 10% | 20% | 30% | 30% | 22%
| Build & code | 30% | 32% | 55% | 50% | 20%
| Test & quality assurance | 25% | 38% | 60% | 55% | 40%
| Release & deploy | 5% | 30% | 50% | 45% | 25%
| Run, monitor & coordinate | 15% | 30% | 40% | 40% | 32%
| Phase mix total (must equal 100%) | 100%
| WEIGHTED AI CEILING |  | 30.4% | 48.25% | 45.25% | 29.5%
D. REALISATION, AND THE NON-AI COMPONENTS — portfolio defaults
| Driver | Year 1 | Year 2 | Year 3 |  | Note
| AI realisation — share of ceiling captured | 25% | 55% | 75% |  | Domain teams may lower this with a stated reason, e.g. a platform on a sunset path.
| Classical ADM productivity (cumulative) | 2% | 5% | 7% |  | Standardisation, defect reduction, shift-left.
| Operating-model productivity (cumulative) | 3% | 6% | 8% |  | Pod consolidation, span of control, one release train.
E. OFFSHORE CEILING
|  | A | B | C | D
| Offshore-able ceiling | 15% | 78% | 85% | 58%
| Applied by policy | 15% | 78% | 0% | 58% |  | Archetype C is held at zero: we take only the onshore Japanese-language roles while MGCC takes engineering.
| Realisation by Year 3 | 93%
F. DERIVED PARAMETERS — what the Golden Inventory looks up
| Archetype | Name | AI ceiling | Productivity by Y3 | Offshore ceiling | Offshore by Y3 | Transition method | Typical duration | Sourcing construct
| A | Language-locked | 30.4% | 33.95% | 15% | 13.95% | Full transition into a Japanese-resident pod; knowledge capture is the critical path | 10-14 weeks per cluster | Fully sourced, onshore-weighted
| B | Offshore-ready | 48.25% | 45.4% | 78% | 72.54% | Full transition, fastest ramp; artefacts already exist | 6-8 weeks per cluster | Fully sourced, moving to output units
| C | MGCC-destined | 45.25% | 43.48% | 0% | 0% | Role handover of onshore roles; MGCC takes engineering directly from the incumbents | 6-8 weeks, role handover | Co-sourced with MGCC, permanently
| D | Legacy-coupled core | 29.5% | 33.37% | 58% | 53.94% | Deepest and slowest; design truth recovered from source, schedulers and job logs | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired

## Golden Inventory
Golden inventory — 142 applications, archetype derived live from the source fields
Columns K, L and M are the only three fields the rule reads. Columns W to AJ are formulas. Column Y is the only place to type.
# | EAI ID | Application | Application long name | 領域 (domain) | Group | Team | Application class | Business critical | Hosting | PRIMARY CODE LANGUAGE | PRIORITY TRANSFER | CLOUD INDICATOR | Cloud platform | Source code owner | Current FTC | Current FTE | Current MGCC | Total effort | % of PRJ | Target FTC | Target FTE/MGCC | Rule fired | Derived archetype | OVERRIDE | FINAL ARCHETYPE | Archetype name | Evidence — what decided it | Why this archetype | AI ceiling | Productivity by Y3 | Offshore ceiling | Offshore by Y3 | Transition method | Typical duration | Sourcing construct
1 | 9629 | Global Sales Comp - Japan | Global Sales Comp - Japan | Fee Management | Core Insurance Systems Group 34956 | Commission Systems Team 34958 | Core Business Application | N | Yes | Other#Infomatica workflow Bash shell Dos batch | N | Yes | Software as a Service (SaaS) | Non-MetLife Owned Application Code (3rd party/COTS) | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
2 | 9796 | LC POSPMC MF-JPN | LifeComm POSPMC | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | Assembler, COBOL, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 59.559 | 7.7542 | 0 | 67.3131 | 71.18% | 33.6566 | 33.6566 | Rule 1 | D |  | D | Legacy-coupled core | Language: Assembler, COBOL, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
3 | 9800 | LC Billing MF-JPN | LifeComm Billing | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, Assembler, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 20.8922 | 1.8538 | 0 | 22.7459 | 94.29% | 11.373 | 11.373 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, Assembler, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
4 | 9801 | LC Collection MF-JPN | LifeComm Collection | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, Assembler, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, Assembler, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
5 | 9802 | LC Corresponding MF-JPN | LifeComm Corresponding | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, Assembler, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 15.9536 | 1.6542 | 0 | 17.6078 | 98.29% | 8.8039 | 8.8039 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, Assembler, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
6 | 9803 | LC UWI MF-JPN | LifeComm UWI | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | Assembler, COBOL, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 8.8046 | 0.85 | 0 | 9.6546 | 94.82% | 4.8273 | 4.8273 | Rule 1 | D |  | D | Legacy-coupled core | Language: Assembler, COBOL, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
7 | 9804 | LC AAPerf MF-JPN | LifeComm AgentAgencyPerformance | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, Assembler, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 10.7842 | 0.74583 | 0 | 11.53 | 83.3% | 5.765 | 5.765 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, Assembler, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
8 | 9805 | LC Payment MF-JPN | LifeComm Payment | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, Assembler, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 2.8967 | 0.025 | 0 | 2.9217 | 90.59% | 1.4608 | 1.4608 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, Assembler, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
9 | 9806 | LC GL/SC MF-JPN | LifeComm GL/SC | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, Assembler, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 5.2888 | 1.025 | 0 | 6.3138 | 83.77% | 3.1569 | 3.1569 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, Assembler, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
10 | 9807 | LC Valuation MF-JPN | LifeComm Valuation | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | N | Yes | COBOL, Assembler, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 9.7688 | 1.4833 | 0 | 11.2521 | 85.63% | 5.626 | 5.626 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, Assembler, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
11 | 9808 | LC AACOMP MF-JPN | LifeComm AgentAgencyComp | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, Assembler, MU(EASYPLUS), JCL | N | No |  | MetLife Owned Application Code | 13.5457 | 3.1437 | 0 | 16.6895 | 72.66% | 8.3447 | 8.3447 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, Assembler, MU(EASYPLUS), JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
12 | 9810 | Processor-I MF-JPN | Claim payment (Processor-I) | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 7.6683 | 1.1292 | 0 | 8.7975 | 75.56% | 4.3988 | 4.3988 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
13 | 9811 | LC Submit MF-JPN | Submit Online | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 1.9683 | 0.16458 | 0 | 2.1329 | 95.31% | 1.0665 | 1.0665 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
14 | 9813 | LC Micro MF-JPN | Micro-Index | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 2.1175 | 0 | 0 | 2.1175 | 64.58% | 1.0588 | 1.0588 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
15 | 9814 | Foreign MF-JPN | Foreign | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | N | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
16 | 9816 | CT Salary MF-JPN | CT Salary System | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 0.2 | 0 | 0 | 0.2 | 0% | 0.1 | 0.1 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
17 | 9817 | TaxCertification MF-JPN | TaxCertification | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | N | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 1.6649 | 0 | 0 | 1.6649 | 40.75% | 0.83244 | 0.83244 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
18 | 9818 | SWINGMANAGER MF-JPN | SWING MANAGER | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | N | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
19 | 9819 | PremCollectDBMF-JPN | Premium Collection History DB | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | N | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
20 | 9820 | MCFA CP DB MF-JPN | MCFA Coupon DB | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
21 | 9821 | Maturity MF-JPN | Payment maturity existing benefit etc | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 4.3783 | 0.97083 | 0 | 5.3492 | 62.61% | 2.6746 | 2.6746 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
22 | 9822 | LC Reins MF-JPN | Reinsurance | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | N | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 6.0129 | 0.25417 | 0 | 6.2671 | 78.99% | 3.1335 | 3.1335 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
23 | 9823 | ASP Bridge(H) MF-JPN | ASP Bridge (HOST) | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Common Service Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 6.7267 | 1.4625 | 0 | 8.1892 | 72.81% | 4.0946 | 4.0946 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
24 | 9824 | CCA MF-JPN | Client Contract Administration | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 1.6308 | 0 | 0 | 1.6308 | 38.68% | 0.81542 | 0.81542 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
25 | 9833 | C04NWC-JPN | CenterServer | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Core Business Application | N | Yes | C/C++ | N | No |  | MetLife Owned Application Code | 8.7317 | 0.11042 | 0 | 8.8421 | 91.69% | 4.421 | 4.421 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
26 | 9834 | C03WRE-JPN | POS Workflow Payment Workflow (Restoring cancelled | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | Y | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.2 | 0.2 | 0 | 0.37083 | 32.58% | 0.18542 | 0.18542 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
27 | 9835 | C12WNC-JPN | POS Workflow Payment Workflow (Claim Transaction A | Insurance Claims and Benefits Payment Related | Customer Service and Operations Systems Group 34965 | Claims Team 34968 | Core Business Application | Y | Yes | VB.NET; C/C++; JAVA | N | No |  | MetLife Owned Application Code | 29.3799 | 5.6167 | 0 | 34.9965 | 90.52% | 17.4983 | 17.4983 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
28 | 9836 | C03WRD-JPN | POS Workflow Payment Workflow (Reduction of paymen | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | Y | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.3 | 0.3 | 0 | 2.5258 | 90.1% | 1.2629 | 1.2629 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
29 | 9842 | C03PCA-JPN | Add Coverage | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | N | Yes | VB | N | No |  | MetLife Owned Application Code | 0.3 | 0.3 | 0 | 2.8862 | 90.3% | 1.4431 | 1.4431 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
30 | 9843 | C10CSS-JPN | FSC Call Support | Customer Care / Call Center Related | Customer Service and Operations Systems Group 34965 | Customer Care Team 34969 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 1.2121 | 0.20833 | 0 | 1.4204 | 63.6% | 0.71021 | 0.71021 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
31 | 9844 | C04VAS-JPN | Voucher Approval System for AS400 | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | Y | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.67083 | 0.68333 | 0 | 1.3542 | 36.92% | 0.67708 | 0.67708 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
32 | 9845 | C04SYM-JPN | Renewal symap Business Work Flow | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 3.4049 | 0 | 0 | 3.4049 | 84.09% | 1.7025 | 1.7025 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
33 | 9846 | C03VSV-JPN | Variable Annuity Sun View | Customer Care / Call Center Related | Customer Service and Operations Systems Group 34965 | Customer Care Team 34969 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.03125 | 0.4 | 0 | 0.43125 | 92.75% | 0.21563 | 0.21563 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
34 | 9847 | PinID tool_JPN | PinID Increase tool | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.15263 | 0.3 | 0 | 0.45262 | 100% | 0.22631 | 0.22631 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
35 | 9848 | C11VCM-JPN | Deposit Control System | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.88542 | 0 | 0 | 0.88542 | 83.06% | 0.44271 | 0.44271 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
36 | 9849 | C04OSI-JPN | S Sum Total System(Open) | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Common Service Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 5.1862 | 0.38333 | 0 | 5.5696 | 83.15% | 2.7848 | 2.7848 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
37 | 9851 | W03FIC-JPN | Guidance Refusal Information Administration System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 0.29167 | 0.11667 | 0 | 0.40833 | 82.65% | 0.20417 | 0.20417 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
38 | 9852 | C03APO-JPN | Apollocs | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | Other#APOLLOCS | N | No |  | Non-MetLife Owned Application Code (3rd party/COTS) | 0.50833 | 0 | 0 | 0.50833 | 36.89% | 0.25417 | 0.25417 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
39 | 9854 | Z04IMA-JPN | Image Search | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Core Business Application | N | Yes | CSS; JAVA;HTML; VB.NET | N | No |  | MetLife Owned Application Code | 1.4004 | 0 | 0 | 1.4004 | 92.86% | 0.70021 | 0.70021 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
40 | 9857 | W05AMS-JPN | Annuity Information Management System(AIMS) | Insurance Claims and Benefits Payment Related | Customer Service and Operations Systems Group 34965 | Claims Team 34968 | Core Business Application | Y | Yes | JAVA | N | No |  | MetLife Owned Application Code | 20.2117 | 1.8167 | 0 | 22.0283 | 92.55% | 11.0142 | 11.0142 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
41 | 9858 | W02OPS-JPN | Insurance Planning for Operator | Marketing/Direct Business Related | Customer and Channel Engineering 34961 |  | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 4.8333 | 1 | 1.0833 | 6.9167 | 71.08% | 3.4583 | 3.4583 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
42 | 9861 | W04RRE-JPN | Rule Engine | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Core Business Application | Y | Yes | JAVA | N | No |  | MetLife Owned Application Code | 6.3153 | 0 | 0 | 6.3153 | 87.33% | 3.1576 | 3.1576 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
43 | 9879 | W03PIU-JPN | IS universal life insurance simulation | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.2 | 0.1 | 0 | 0.30833 | 67.57% | 0.15417 | 0.15417 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
44 | 9890 | W08HTN-JPN | conservation contact personnel entry system | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 1.5055 | 0.045833 | 0 | 1.5513 | 7.201% | 0.77565 | 0.77565 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
45 | 9894 | W08NAV-JPN | Branch Marketing Information System | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution F2F Team 34962 | Core Business Application | N | Yes | VB | N | No |  | MetLife Owned Application Code | 2.8419 | 0.35208 | 0 | 3.194 | 79.19% | 1.597 | 1.597 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
46 | 9896 | W08SFE-JPN | commission Inquiry | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 1.0914 | 0.105 | 0 | 1.1964 | 98.96% | 0.59819 | 0.59819 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
47 | 9899 | W08CIS-JPN | Career Information System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 1.2041 | 0.52917 | 0 | 1.7333 | 82.69% | 0.86665 | 0.86665 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
48 | 9906 | W08NAR-JPN | producers information entry system | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 1.286 | 0.14542 | 0 | 1.4315 | 95.05% | 0.71573 | 0.71573 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
49 | 9907 | W13WWF-JPN | Web work flow | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.38583 | 0 | 0 | 0.38583 | 35.21% | 0.19292 | 0.19292 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
50 | 9910 | P08MMS-JPN | Medical Management System | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.0625 | 0 | 0 | 0.0625 | 100% | 0.03125 | 0.03125 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
51 | 9920 | WPSYEC-JPN | Direct Marketing Site | Marketing/Direct Business Related | Customer and Channel Engineering 34961 | Marketing and Leads Team 34964 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 10.3375 | 3.5583 | 5.1817 | 19.0775 | 93.36% | 9.5388 | 9.5388 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
52 | 9921 | W07IPC-JPN | Internet Prospective Information | Marketing/Direct Business Related | Customer and Channel Engineering 34961 | Marketing and Leads Team 34964 | Core Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 0.30417 | 0.041667 | 0 | 0.34583 | 100% | 0.17292 | 0.17292 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
53 | 9926 | W01LOI-JPN | Japan Authorization / login | Common Service Platform | Japan Platform Team 35775 | Japan Platform Team 35775 | Common Service Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.075 | 0 | 0 | 0.075 | 0% | 0.0375 | 0.0375 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
54 | 9928 | W01MAS-JPN | Common Framework(Master4) | Common Service Platform | Japan Platform Team 35775 | Japan Platform Team 35775 | Common Service Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 1.3971 | 1 | 0 | 2.3971 | 86.44% | 1.1985 | 1.1985 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
55 | 9930 | A04MMP-JPN | AS400 Mass Marketing System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | Y | Yes | Other#RPG | N | No |  | MetLife Owned Application Code | 2.4083 | 0.075 | 0 | 2.4833 | 89.93% | 1.2417 | 1.2417 | Rule 1 | D |  | D | Legacy-coupled core | Language: Other#RPG | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
56 | 9931 | P02BKE-JPN | Sales illustration system (based on EXCEL) for BAN | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution Banca Team 34963 | Core Business Application | N | Yes | Other#VBA | N | No |  | MetLife Owned Application Code | 13 | 2.275 | 0 | 15.275 | 91.73% | 7.6375 | 7.6375 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
57 | 9940 | WPSC2S-JPN | Call Control System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.3875 | 0.025 | 0 | 0.4125 | 81.82% | 0.20625 | 0.20625 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
58 | 9941 | B13ITS-JPN | ITS-PCIS(Mutual Fund System(Including Bestway) | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | Yes | Software as a Service (SaaS) | MetLife Owned Application Code | 0.92916 | 0.0875 | 0 | 1.0167 | 41.31% | 0.50833 | 0.50833 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
59 | 9947 | W13WEP-JPN | Web Payment | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | Y | Yes | JAVA | N | No |  | MetLife Owned Application Code | 9 | 1.1542 | 0 | 10 | 75.9% | 5 | 5 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
60 | 9948 | Data Send System for BANC MF-JP | Data Send System for BANC | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 9.2697 | 2.8458 | 0 | 12.1155 | 77.13% | 6.0578 | 6.0578 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
61 | 9949 | CCMDNT-JPN | .NET Common Infrastructure | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Common Service Business Application | N | Yes | VB.NET; C # | N | No |  | MetLife Owned Application Code | 0.066667 | 0 | 0 | 0.066667 | 0% | 0.033333 | 0.033333 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
62 | 9951 | BCMHRP-JPN | Data cooperation | Data Infrastructure | Data Platforms Team 34980 | Data Platforms Team 34980 | Common Service Business Application | N | Yes | Other#MS-DOS ,AWK,VBScript,JAVA | Y | No | Running on both on-premises and Azure. The on-premises version will be decommissioned by the end of 2027. | MetLife Owned Application Code | 7 | 1 | 0 | 7.927 | 77.92% | 3.9635 | 3.9635 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
63 | 9962 | WPSCUS-JPN | Customer Support System | Marketing/Direct Business Related | Customer and Channel Engineering 34961 | Marketing and Leads Team 34964 | Core Business Application | N | Yes | JavaScript; Other#APEX | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 8.9217 | 2.4104 | 1.52 | 12.8521 | 82.74% | 6.426 | 6.426 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
64 | 9964 | WAANSO-JPN | New Submit Online System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 1.9533 | 0.3625 | 0 | 2.3158 | 90.82% | 1.1579 | 1.1579 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
65 | 9965 | WZZHYO-JPN | Report Template Management System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.025 | 0.0375 | 0 | 0.0625 | 20% | 0.03125 | 0.03125 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
66 | 9969 | EAADRS-JPN | Dr.SUM | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | Non-MetLife Owned Application Code (3rd party/COTS) | 0.31238 | 0.025 | 0 | 0.33737 | 67.58% | 0.16869 | 0.16869 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
67 | 9975 | WPMWCC-JPN | Web Contact Center | Customer Care / Call Center Related | Customer Service and Operations Systems Group 34965 | Customer Care Team 34969 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 1.1117 | 0 | 0 | 1.1117 | 58.51% | 0.55583 | 0.55583 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
68 | 9977 | WGLRPC-JPN | ReportConnection | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution F2F Team 34962 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 1 | 1 | 0 | 0.45792 | 0% | 0.22896 | 0.22896 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
69 | 9980 | Policy UWIBATCH MF-JPN | Policy Underwriting and Issue Batch | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | Other#ASM; Cobol | N | No |  | MetLife Owned Application Code | 12.6069 | 1.1417 | 0 | 13.7485 | 81.5% | 6.8743 | 6.8743 | Rule 1 | D |  | D | Legacy-coupled core | Language: Other#ASM; Cobol | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
70 | 9983 | WAAATF-JPN | Agents Target Following system | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution F2F Team 34962 | Core Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 6.6142 | 0.64792 | 0 | 7.2621 | 93.91% | 3.631 | 3.631 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
71 | 9986 | ZGLEST-JPN | eSTATION | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JavaScript; VB.NET; C#;HTML | N | No |  | MetLife Owned Application Code | 2.4427 | 0.57083 | 0 | 3.0135 | 27.52% | 1.5068 | 1.5068 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
72 | 9992 | CMESB-JPN | Enterprise Service Bus | Common Service Platform | Japan Platform Team 35775 | Japan Platform Team 35775 | Common Service Business Application | N | Yes | JAVA; Other#ESQL | N | No |  | MetLife Owned Application Code | 7.2083 | 2.9958 | 2.5208 | 12.725 | 93.78% | 6.3625 | 6.3625 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
73 | 9994 | WPMAUD-JPN | Unknown Address Tracking System | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | N | No | JAVA | N | Yes | Platform as a Service (PaaS) | Non-MetLife Owned Application Code (3rd party/COTS) | 0.8 | 0.2 | 0 | 1.1729 | 42.81% | 0.58646 | 0.58646 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
74 | 9995 | WCMPXS-JPN | ProductXpress | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Infrastructure Application | N | Yes | Other#Peculiar Language, Implemented in PX designer. | N | No |  | MetLife Owned Application Code | 0.77917 | 0 | 0 | 0.77917 | 67.91% | 0.38958 | 0.38958 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
75 | 9996 | WUIURE-JPN | Pre-Underwriting | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.22625 | 0 | 0 | 0.22625 | 33.7% | 0.11313 | 0.11313 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
76 | 9999 | LINC MF-JPN | LINC | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | Y | Yes | COBOL, MU(EASYPLUS), Assembler, JCL | N | No |  | MetLife Owned Application Code | 1.0288 | 0 | 0 | 1.0288 | 12.92% | 0.51438 | 0.51438 | Rule 1 | D |  | D | Legacy-coupled core | Language: COBOL, MU(EASYPLUS), Assembler, JCL | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
77 | 10001 | A06TOG-JPN | Group Policy Management System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | Y | Yes | Other#RPG; Cobol | N | No |  | MetLife Owned Application Code | 2.7292 | 3.025 | 0 | 5.7542 | 34.54% | 2.8771 | 2.8771 | Rule 1 | D |  | D | Legacy-coupled core | Language: Other#RPG; Cobol | Rules hard-coded across modules and design truth is not written down. AI does comprehension here, not generation. | 29.5% | 33.37% | 58% | 53.94% | 14-20 weeks per cluster | Fully sourced, MetLife SMEs paired | 0
78 | 10032 | W06TGR-JPN | Group Policy Inquiry System for Intranet | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | Y | Yes | VB.NET; JAVA | N | No |  | MetLife Owned Application Code | 1.8583 | 0.94167 | 0 | 2.8 | 26.93% | 1.4 | 1.4 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
79 | 11004 | WAAICM-JPN | ICM | Fee Management | Core Insurance Systems Group 34956 | Commission Systems Team 34958 | Core Business Application | N | Yes | JAVA; C#; Other#ETL JAVA(ADJP) SQL | N | Yes | Software as a Service (SaaS) | MetLife Owned Application Code | 21.5061 | 7.7292 | 0 | 29.2353 | 83.1% | 14.6176 | 14.6176 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
80 | 11005 | WAACPS-JPN | Commission and Performance System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 0.3625 | 0.041667 | 0.5 | 0.90417 | 44.7% | 0.45208 | 0.45208 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
81 | 11007 | OMSIKN-JPN | Conservation contract transferring system | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.23492 | 0.072917 | 0 | 0.30783 | 95.94% | 0.15392 | 0.15392 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
82 | 11008 | OMSTAT-JPN | Conservation contract allowance system | Marketing/Direct Business Related | Customer and Channel Engineering 34961 | Marketing and Leads Team 34964 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.13542 | 0.016667 | 0 | 0.15208 | 52.05% | 0.076042 | 0.076042 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
83 | 11010 | ZGLEDQ-JPN | FATCA Oracle EDQ | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA; C # | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 1.2583 | 0.029167 | 0.5 | 1.7875 | 55.71% | 0.89375 | 0.89375 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
84 | 11011 | WGLWLF-JPN | Watch List Filtering system | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 6.0792 | 1.0708 | 0 | 7.15 | 90.38% | 3.575 | 3.575 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
85 | 11012 | WZZMNB-JPN | My number management system | Insurance Claims and Benefits Payment Related | Customer Service and Operations Systems Group 34965 | Claims Team 34968 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 1.6523 | 0.29167 | 0 | 1.944 | 83.22% | 0.972 | 0.972 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
86 | 11014 | BCMETL-JPN | Informatica Platform | Data Infrastructure | Data Platforms Team 34980 | Data Platforms Team 34980 | Common Service Business Application | N | Yes | Other#Used UI for development and stored data as XML | Y | Yes |  | MetLife Owned Application Code | 29.0979 | 6.825 | 6.85 | 42.7729 | 88.28% | 21.3865 | 21.3865 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
87 | 11203 | WPSCFC-JPN | c-Force | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution F2F Team 34962 | Core Business Application | N | No | Other#APEX;HTML; JavaScript | Y | Yes | Software as a Service (SaaS) | Non-MetLife Owned Application Code (3rd party/COTS) | 20.8333 | 10.0042 | 12.725 | 43.5625 | 86.92% | 21.7812 | 21.7812 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
88 | 11288 | CGLFJM-JPN | Misconduct Management system | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | VB | N | No |  | MetLife Owned Application Code | 0.091667 | 0 | 0 | 0.091667 | 27.27% | 0.045833 | 0.045833 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
89 | 11308 | WGLBSR-JPN | BSRec | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.48125 | 0.0625 | 0 | 0.54375 | 37.93% | 0.27187 | 0.27187 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
90 | 11604 | JP-RPASS | JAPAN_BluePrism RPA | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Common Service Business Application | N | Yes | Other#COTS from BluePrism | N | No |  | Non-MetLife Owned Application Code (3rd party/COTS) | 5.6625 | 4.075 | 0 | 9.7375 | 89.73% | 4.8687 | 4.8687 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
91 | 11893 | W03CCP-JPN | Customer Communication Preferences | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 0.2 | 0.2 | 0 | 0.35417 | 56.47% | 0.17708 | 0.17708 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
92 | 11986 | JP-Banca Report | Japan Banca Report | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution Banca Team 34963 | Common Service Business Application | N | Yes | JAVA | N | Yes | Infrastructure as a Service (IaaS); Platform as a Service (PaaS) | MetLife Owned Application Code | 6 | 6 | 3 | 15 | 100% | 7.5 | 7.5 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Infrastructure as a Service (IaaS); Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
93 | 12021 | LPS-JPN(EUC081) | Life Plan Simulation Japan | Marketing/Direct Business Related | Customer and Channel Engineering 34961 | Marketing and Leads Team 34964 | Core Business Application | N | Yes | PHP | N | No |  | Non-MetLife Owned Application Code (3rd party/COTS) | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
94 | 12030 | CIT-JPN(EUC082) | Inheritance Tax Simulation | Marketing/Direct Business Related | Customer and Channel Engineering 34961 | Marketing and Leads Team 34964 | Core Business Application | N | Yes | JAVA | N | No |  | Non-MetLife Owned Application Code (3rd party/COTS) | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
95 | 12038 | CMIAPI-JPN | API Hub | Common Service Platform | Japan Platform Team 35775 | Japan Platform Team 35775 | Common Service Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 19.2467 | 4.1333 | 16.9104 | 40.2904 | 94.85% | 20.1452 | 20.1452 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
96 | 12117 | K2 | Japan K2 - Digital Workflows | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | Y | Yes | VB.NET | N | No |  | Non-MetLife Owned Application Code (3rd party/COTS) | 6 | 15.5375 | 11 | 62.6424 | 86.32% | 31.3212 | 31.3212 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
97 | 12198 | JP-PCI-RPASS | Japan PCI Robotics Process Automation Service | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Common Service Business Application | N | Yes | Other#This is coded within blueprism | N | No |  | Non-MetLife Owned Application Code (3rd party/COTS) | 1 | 2 | 0 | 3 | 0% | 1.5 | 1.5 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
98 | 12520 | RBRARS-JPN | RBWF Report Automatic Recognition System | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Core Business Application | N | Yes | JAVA | N | Yes |  | MetLife Owned Application Code | 0.125 | 0 | 0 | 0.125 | 100% | 0.0625 | 0.0625 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes () | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
99 | 12527 | CMEAPI-JP | Japan Partner API | Common Service Platform | Japan Platform Team 35775 | Japan Platform Team 35775 | Common Service Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 0.10833 | 0 | 0.025 | 0.13333 | 100% | 0.066667 | 0.066667 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
100 | 12607 | JP-WCMAUT | JP Authentication Platform | Common Service Platform | Japan Platform Team 35775 | Japan Platform Team 35775 | Common Service Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 1.3375 | 0 | 1 | 2.3375 | 100% | 1.1687 | 1.1687 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
101 | 12646 | Himawari | Himawari (Call Center Platform) | Customer Care / Call Center Related | Customer Service and Operations Systems Group 34965 | Customer Care Team 34969 | Core Business Application | Y | No | JavaScript;HTML; Other#APEX | N | Yes | Software as a Service (SaaS) | Non-MetLife Owned Application Code (3rd party/COTS) | 9.5833 | 11.3375 | 7.0833 | 28.0042 | 81.22% | 14.0021 | 14.0021 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
102 | 12654 | JP-QA Shared Service | Japan QA Shared Service- multiple projects | Common Service Platform | Customer Service and Operations Systems Group 34965 |  | Platform | N | Yes | Other#Selenese, but supports others | N | No |  | MetLife Owned Application Code | 0 | 0.25 | 0 | 0.25 | 100% | 0.125 | 0.125 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
103 | 12675 | JP-DB2-CONNECT | Japan DB2 Connect Proxy | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Platform | N | Yes | Other#COTS | N | No |  | Non-MetLife Owned Application Code (3rd party/COTS) | 0 | 0.1 | 0 | 0.1 | 0% | 0.05 | 0.05 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
104 | 12721 | JP-Payroll | Japan Payroll System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | No | Other# N-A(SaaS) | N | Yes | Software as a Service (SaaS) | Non-MetLife Owned Application Code (3rd party/COTS) | 0.24167 | 0 | 0 | 0.24167 | 93.1% | 0.12083 | 0.12083 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
105 | 12820 | JP-OLB Batch | Japan - Direct Marketing Batch Applications | Marketing/Direct Business Related | Customer and Channel Engineering 34961 | Marketing and Leads Team 34964 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.3625 | 0 | 0 | 0.3625 | 100% | 0.18125 | 0.18125 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
106 | 12890 | ASP B_O-JPN | ASP Bridge (OPEN) | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Common Service Business Application | Y | Yes | JAVA; C#; VB.NET | N | No |  | MetLife Owned Application Code | 1.2346 | 0.0625 | 0 | 1.2971 | 85.06% | 0.64856 | 0.64856 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
107 | 12894 | WCMCCMJPN | Inspire - Forms Management | Customer Care / Call Center Related | Customer Service and Operations Systems Group 34965 | Customer Care Team 34969 | Common Service Business Application | N | Yes | JavaScript | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 2.6333 | 2.7792 | 2.9188 | 8.3313 | 92.75% | 4.1656 | 4.1656 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
108 | 12932 | Digital Portal | Digital Portals for Policy Administration | Customer Care / Call Center Related | Customer Service and Operations Systems Group 34965 | Customer Care Team 34969 | Core Business Application | N | Yes | JAVA; JavaScript | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 35.8196 | 25 | 12.8667 | 73.6863 | 91.17% | 36.8431 | 36.8431 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
109 | 12991 | JP - Remote Closing | JP - Remote Sales Closing | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution F2F Team 34962 | Common Service Business Application | N | Yes | JAVA | Y | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 4.6458 | 4.5625 | 3 | 12.2083 | 100% | 6.1042 | 6.1042 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
110 | 13139 | PaymentService | Payment Common Service - JP | Common Service Platform | Japan Platform Team 35775 | Japan Platform Team 35775 | Common Service Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 0 | 1.3 | 0.69167 | 1.9917 | 100% | 0.99583 | 0.99583 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
111 | 13197 | JP-GSSP | Japan Sales Platform (GSSP) | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution F2F Team 34962 | Core Business Application | Y | Yes | JAVA; JavaScript | Y | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 151.7708 | 30.9375 | 47.2042 | 229.9125 | 94.72% | 114.9562 | 114.9562 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
112 | 13262 | Business Content Management | Business Content Management | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Common Service Business Application | N | No | Other#n/a | N | Yes | Software as a Service (SaaS); Platform as a Service (PaaS) | Non-MetLife Owned Application Code (3rd party/COTS) | 1.5133 | 1.75 | 0.5 | 3.7633 | 21.15% | 1.8817 | 1.8817 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS); Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
113 | 13274 | DSP | Digital Servicing Platform | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Platform | N | Yes | PL/SQL | N | No |  | MetLife Owned Application Code | 0 | 1 | 0 | 1 | 100% | 0.5 | 0.5 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
114 | 13314 | JDPREP | Japan Data Platform and Reporting-JP | Data Infrastructure | Data Platforms Team 34980 | Data Platforms Team 34980 | Platform | N | Yes | Other#Transact SQL | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 28.6067 | 11 | 9.1417 | 50.065 | 86.26% | 25.0325 | 25.0325 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
115 | 13405 | Kintone-JPN | kintone and paperlogic electronic contract system | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Common Service Business Application | N | No | Other#Vendor Managed | N | Yes | Software as a Service (SaaS) | Non-MetLife Owned Application Code (3rd party/COTS) | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
116 | 13453 | POS-IMS | POS - Integrated Management System | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Platform | N | Yes | VB.NET; JAVA | N | No |  | MetLife Owned Application Code | 0.9 | 0.3 | 0 | 9.9375 | 90.44% | 4.9688 | 4.9688 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
117 | 13476 | AppsPortal | Enterprise Apps Portal | Common Service Platform | Customer Service and Operations Systems Group 34965 |  | Core Business Application | N | Yes | JavaScript; JAVA | Y | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 57.1499 | 23.3021 | 42.0867 | 122.5386 | 88.08% | 61.2693 | 61.2693 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
118 | 13500 | Scan Manager | Digital Scan Manager | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | N | Yes | VB.NET | N | No |  | Non-MetLife Owned Application Code (3rd party/COTS) | 0.5 | 0.2 | 0 | 0.59583 | 66.43% | 0.29792 | 0.29792 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
119 | 13676 | ODMoC | IBM Operational Decision Manager on Cloud | Common Service Platform | Japan Platform Team 35775 | Japan Platform Team 35775 | Core Business Application | N | No | Other#IRL Vendor supported language | N | Yes | Software as a Service (SaaS) | MetLife Owned Application Code | 11.5729 | 2.3333 | 2.1354 | 16.0417 | 93.77% | 8.0208 | 8.0208 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
120 | 13721 | External Portal | External Apps Portal | Fee Management | Core Insurance Systems Group 34956 | Commission Systems Team 34958 | Core Business Application | N | Yes | JAVA; JavaScript | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 1.6667 | 0.70833 | 0.58333 | 2.9583 | 91.55% | 1.4792 | 1.4792 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
121 | 13738 | Distribution Systems - Internal | Distribution Systems - Internal | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution F2F Team 34962 | Core Business Application | N | No | JAVA | Y | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 0.33333 | 0.25 | 0.083333 | 0.66667 | 100% | 0.33333 | 0.33333 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
122 | 13812 | Corporate Batch | OpenBatch system for Corporate | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 2.04 | 1.7 | 0 | 3.74 | 30.84% | 1.87 | 1.87 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
123 | 13820 | Claim Batch | OpenBatch system for Claim | Insurance Claims and Benefits Payment Related | Customer Service and Operations Systems Group 34965 | Claims Team 34968 | Common Service Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 20.5904 | 5.0458 | 18.1458 | 43.7821 | 98.37% | 21.891 | 21.891 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
124 | 13856 | Customer Care Batch | Open Batch System for Customer Care | Customer Care / Call Center Related | Customer Service and Operations Systems Group 34965 | Customer Care Team 34969 | Core Business Application | N | Yes | Other#ETL (Infomatica) | N | No |  | MetLife Owned Application Code | 4.4025 | 1.9583 | 0.041667 | 6.4025 | 95.77% | 3.2012 | 3.2012 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
125 | 13863 | AURA | AURA Underwriting | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Common Service Business Application | N | No | JAVA | N | Yes | Software as a Service (SaaS) | Non-MetLife Owned Application Code (3rd party/COTS) | 1 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
126 | 13884 | POS Batch | OpenBatch system for Policy Servicing | Storage and Preservation Related | Customer Service and Operations Systems Group 34965 | Policy Servicing Team 34967 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.4 | 0.3 | 0 | 4.2762 | 90.91% | 2.1381 | 2.1381 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
127 | 13888 | Distribution Marketing batches | Distribution Marketing related batches | Marketing/Direct Business Related | Customer and Channel Engineering 34961 | Marketing and Leads Team 34964 | Common Service Business Application | N | Yes | PL/SQL | N | No |  | MetLife Owned Application Code | 2.9475 | 0.5 | 1 | 4.4475 | 24.08% | 2.2238 | 2.2238 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
128 | 13971 | HIMAWARI backend apps | HIMAWARI backend applications | Customer Care / Call Center Related | Customer Service and Operations Systems Group 34965 | Customer Care Team 34969 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.95417 | 0.55 | 0 | 1.5042 | 29.36% | 0.75208 | 0.75208 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
129 | 13982 | New Business Batch | OpenBatch system for New Business | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 0.86917 | 0.033333 | 0 | 0.9025 | 100% | 0.45125 | 0.45125 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
130 | 14049 | WCC | Web Credit Card | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution F2F Team 34962 | Common Service Business Application | N | Yes | JAVA; HTML5; JavaScript | Y | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 0 | 0 | 0.125 | 0.125 | 100% | 0.0625 | 0.0625 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
131 | 14059 | PDF Auto Loader Batch | Open Batch System for PDF Auto Loader | contract management | Core Insurance Systems Group 34956 | Policy Admin Systems Team 34957 | Core Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 1.0167 | 0.010417 | 0 | 1.0271 | 90.26% | 0.51354 | 0.51354 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
132 | 14097 | IVR Tekigosei | Confirming UnitLink product suitability via IVR | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution F2F Team 34962 | Common Service Business Application | N | No | Other# N-A | Y | Yes | Software as a Service (SaaS) | Non-MetLife Owned Application Code (3rd party/COTS) | 0.083333 | 0 | 0.083333 | 0.16667 | 100% | 0.083333 | 0.083333 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
133 | 14217 | W09WSD-JPN BIS | Call Center WSD BIS | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 | Distribution Banca Team 34963 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.80833 | 0.075 | 0 | 0.88333 | 48.11% | 0.44167 | 0.44167 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
134 | 14267 | NBAPPS-JPN | New Business Operation Apps | New Contract Related | Customer Service and Operations Systems Group 34965 | New Business Team 34966 | Common Service Business Application | N | Yes | JAVA | N | No |  | MetLife Owned Application Code | 12.2567 | 0.5 | 0 | 12.7567 | 88.24% | 6.3783 | 6.3783 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
135 | 14285 | SCS | Sales Compensation System | Fee Management | Core Insurance Systems Group 34956 | Commission Systems Team 34958 | Core Business Application | N | Yes | JAVA; Other#SQL | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 14.975 | 1.3417 | 0 | 16.3167 | 98.77% | 8.1583 | 8.1583 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
136 | 14322 | Pega for Claims | Pega for Claims - Pega Workflow | Insurance Claims and Benefits Payment Related | Customer Service and Operations Systems Group 34965 | Claims Team 34968 | Core Business Application | N | No | JAVA | N | Yes | Software as a Service (SaaS) | MetLife Owned Application Code | 11.4917 | 0.70833 | 4.5 | 16.7 | 98.7% | 8.35 | 8.35 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Software as a Service (SaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
137 | 14376 | RAPS | Retirement Allowance Payment System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.27479 | 0 | 0 | 0.27479 | 77.26% | 0.1374 | 0.1374 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
138 | 14377 | Commission System Support Tool | Support Tool for Commission System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 0.59708 | 0.12917 | 0 | 0.72625 | 97.99% | 0.36312 | 0.36312 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
139 | 14423 | MDRS | Maturity and Deferral Related System | Insurance Claims and Benefits Payment Related | Customer Service and Operations Systems Group 34965 | Claims Team 34968 | Core Business Application | Y | Yes | VB.NET | N | No |  | MetLife Owned Application Code | 2.1225 | 0 | 0 | 2.1225 | 75.07% | 1.0613 | 1.0613 | Rule 4 | A |  | A | Language-locked | Cloud Indicator = No, not mainframe, not a transfer target | On-premises and non-mainframe, so the constraint is not the technology — it is that the business context exists only in Japanese, in few heads. | 30.4% | 33.95% | 15% | 13.95% | 10-14 weeks per cluster | Fully sourced, onshore-weighted | 0
140 | 14595 | JP-BANCA | Japan Sales Platform-BANCA | Sales / Insurance Recruitment | Customer and Channel Engineering 34961 |  | Core Business Application | N | Yes | JavaScript; JAVA | Y | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 60 | 25 | 25 | 110 | 99.24% | 55 | 55 | Rule 2 | C |  | C | MGCC-destined | Priority Transfer Target = Y | MetLife has already flagged these for transfer and nine of ten already carry MGCC people. Routing them through a vendor transition pays for the same knowledge transfer twice. | 45.25% | 43.48% | 0% | 0% | 6-8 weeks, role handover | Co-sourced with MGCC, permanently | 0
141 | 14701 | Commission calculation | Commission Calculation Service | Fee Management | Core Insurance Systems Group 34956 | Commission Systems Team 34958 | Common Service Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0
142 | 14930 | Vcalc-JPN | Variable Insurance Guarantee Calculation System | Corporate Related | Core Insurance Systems Group 34956 | Corporate Systems Team 34959 | Core Business Application | N | Yes | JAVA | N | Yes | Platform as a Service (PaaS) | MetLife Owned Application Code | 1.5 | 0.5 | 0 | 2 | 100% | 1 | 1 | Rule 3 | B |  | B | Offshore-ready | Cloud Indicator = Yes (Platform as a Service (PaaS)) | Cloud migration has already forced re-platforming, documentation and specifiability. Highest AI and offshore ceiling in the estate. | 48.25% | 45.4% | 78% | 72.54% | 6-8 weeks per cluster | Fully sourced, moving to output units | 0

## Domain Summary
Domain summary — the starting parameters for every 領域
Each domain team begins here. The weighted ceilings are effort-weighted across that domain's own archetype mix.
| 領域 | Apps | Effort | Share | A | B | C | D | A % | B % | C % | D % | Weighted AI ceiling | Productivity by Y3 | Weighted offshore ceiling
| Common Service Platform | 10 | 198.7803 | 13.22% | 13.05 | 63.1917 | 122.5386 | 0 | 6.565% | 31.79% | 61.65% | 0% | #VALUE! | #VALUE! | #VALUE!
| Corporate Related | 33 | 50.4389 | 3.354% | 32.0797 | 10.1217 | 0 | 8.2375 | 63.6% | 20.07% | 0% | 16.33% | #VALUE! | #VALUE! | #VALUE!
| Customer Care / Call Center Related | 8 | 120.8917 | 8.038% | 10.87 | 110.0217 | 0 | 0 | 8.992% | 91.01% | 0% | 0% | #VALUE! | #VALUE! | #VALUE!
| Data Infrastructure | 3 | 100.765 | 6.7% | 0 | 50.065 | 50.7 | 0 | 0% | 49.68% | 50.32% | 0% | #VALUE! | #VALUE! | #VALUE!
| Fee Management | 5 | 48.5103 | 3.225% | 0 | 48.5103 | 0 | 0 | 0% | 100% | 0% | 0% | #VALUE! | #VALUE! | #VALUE!
| Insurance Claims and Benefits Payment Related | 6 | 121.5735 | 8.083% | 61.0914 | 60.4821 | 0 | 0 | 50.25% | 49.75% | 0% | 0% | #VALUE! | #VALUE! | #VALUE!
| Marketing/Direct Business Related | 9 | 44.1542 | 2.936% | 30.9563 | 13.1979 | 0 | 0 | 70.11% | 29.89% | 0% | 0% | #VALUE! | #VALUE! | #VALUE!
| New Contract Related | 12 | 40.4906 | 2.692% | 40.3656 | 0.125 | 0 | 0 | 99.69% | 0.3087% | 0% | 0% | #VALUE! | #VALUE! | #VALUE!
| Sales / Insurance Recruitment | 13 | 438.714 | 29.17% | 19.8102 | 22.2621 | 396.6417 | 0 | 4.516% | 5.074% | 90.41% | 0% | #VALUE! | #VALUE! | #VALUE!
| Storage and Preservation Related | 15 | 108.9078 | 7.241% | 107.3807 | 1.5271 | 0 | 0 | 98.6% | 1.402% | 0% | 0% | #VALUE! | #VALUE! | #VALUE!
| contract management | 28 | 230.75 | 15.34% | 1.4797 | 0 | 0 | 229.2703 | 0.6413% | 0% | 0% | 99.36% | #VALUE! | #VALUE! | #VALUE!
| PORTFOLIO | 142 | 1503.976 | 100% | 317.0835 | 379.5045 | 569.8803 | 237.5078 | 21.08% | 25.23% | 37.89% | 15.79% | #VALUE! | #VALUE! | #VALUE!
How to read the last three columns
• WEIGHTED AI CEILING — the most productivity this domain could ever earn from AI, if every ceiling were fully realised. It is a property of the estate, not of the plan.
• PRODUCTIVITY BY Y3 — the ceiling put through the portfolio-default realisation curve (75% by Year 3) and compounded with classical and operating-model productivity. This is the number to price against unless you have a stated reason to differ.
• WEIGHTED OFFSHORE CEILING — with archetype C held at zero by policy, because on those applications MGCC takes engineering and we hold only the onshore roles.
• A domain may lower realisation with a documented reason — Data Infrastructure does, because Informatica is on a sunset path. It may not raise the ceiling.

## Archetype Summary
Archetype summary — the portfolio seen four ways
Every figure is a roll-up of the Golden Inventory, so it moves if a classification or an override changes.
| Archetype | Name | Apps | Effort | Share | Current FTC | Current FTE | Current MGCC | AI ceiling | Productivity Y3 | Offshore Y3
| A | Language-locked | 71 | 317.0835 | 21.08% | 195.1087 | 56.3379 | 20.8275 | 30.4% | 33.95% | 13.95%
| B | Offshore-ready | 33 | 379.5045 | 25.23% | 210.597 | 86.4417 | 82.0221 | 48.25% | 45.4% | 72.54%
| C | MGCC-destined | 10 | 569.8803 | 37.89% | 330.9145 | 101.8813 | 137.1575 | 45.25% | 43.48% | 0%
| D | Legacy-coupled core | 28 | 237.5078 | 15.79% | 207.904 | 29.6037 | 0 | 29.5% | 33.37% | 53.94%
|  | Portfolio | 142 | 1503.976 | 100% | 944.5241 | 274.2646 | 240.0071 | 40.39% | 40.36% | 29.76%
Portfolio figures are effort-weighted across the four archetypes.
CHECKS — all three must be zero
| Check | Expected | Actual | Variance
| Applications classified | 142 | 142 | 0
| Effort classified | 1504 | 1503.976 | -0.02395
| Applications with no archetype | 0 | 0 | 0
| Overrides applied |  | 0 |  | Every override must have a matching entry on the Overrides sheet.

## Overrides & Change Log
Overrides and change log
An override changes one application. It never changes the rule. No override is valid without an owner, a date and a reason.
A. APPLICATION OVERRIDES
| EAI ID | Application | From | To | Reason | Raised by | Date | Approved by
Type the override into column Y of the Golden Inventory as well — this sheet is the record, that column is the mechanism.
B. CHANGES TO THE RULE ITSELF
| Date | What changed | Why | Agreed by | Domains re-run
| 2 Sep 2026 | Archetype A / B boundary set to Cloud Indicator | The earlier proxy (Cloud Platform contains SaaS) produced A 10 / B 94, which contradicted Section 4.1. Cloud Indicator reproduces Section 4.1's counts exactly: A 71, B 33. | Solution architecture | All — baseline
C. WHAT REQUIRES AGREEMENT ACROSS ALL DOMAINS
• Any change to the four rules or their order — the rule sets the price, so a change re-prices every domain.
• Any change to the phase mix, the AI-addressable shares, or the offshore ceilings on the Classification Rules sheet.
• Any change to the realisation curve used as the portfolio default. A single domain may deviate downward with a stated reason; the default itself may not move without agreement.