## Slide 1
MLJ CLOUD TRANSFORMATION
Opportunity Assessment
Target EA Inventory Analysis — Prepared to Inform RFP Scope of Work
August 25, 2026

## Slide 2
AGENDA
What's Inside This Assessment
01
Executive Summary & Scope
What's in scope, what's excluded, and the headline numbers
02
Current-State Snapshot
Cloud adoption, technology stack, and ownership profile today
03
Priority Transformation Clusters
Six clusters sized by effort, criticality, and complexity
04
Roadmap, RFP Scope & Risks
Sequencing, vendor capabilities, and what to watch
MLJ Cloud Transformation Opportunity Assessment
2

## Slide 3
EXECUTIVE SUMMARY
Where MLJ Stands Today
114 applications are in scope for this assessment. 72 of them (63%) remain on-premises today, representing 332 of 1273 total FTE-equivalent effort. Applications already migrated account for a disproportionate 74% of effort despite being only 37% of the count — the non-cloud estate is a long tail with no single dominant cluster.
72
Apps Not Yet Cloud
332
FTE-Equiv. Effort (Non-Cloud)
13
Critical Non-Cloud Apps
9
Non-Cloud COTS/3rd-Party
Largest single opportunity: K2 workflow platform (62.6 FTE-equiv, critical) — target architecture already names its successor.
Highest criticality concentration: Insurance Claims & Benefits Payment — 61.1 FTE-equiv across just 4 apps, 3 critical.
MLJ Cloud Transformation Opportunity Assessment
3

## Slide 4
SCOPE EXCLUSION
The Core Policy Administration Mainframe Estate Is Out of Scope
The contract management domain — the mainframe-hosted “LC” / LifeComm policy administration suite (point-of-sale, billing, collections, correspondence, underwriting, payment, GL, agent compensation, valuation, and reinsurance processing on IBM mainframe) — has been excluded from this assessment. Every figure, table, and cluster in this deck describes the remaining in-scope estate only.
28
Applications Excluded
230.7
FTE-Equiv. Effort Excluded
20
Critical Apps Excluded
MLJ Cloud Transformation Opportunity Assessment
4

## Slide 5
CURRENT STATE
Cloud Adoption Snapshot
Chart: Applications by Cloud Status
| Non-Cloud | Cloud-Enabled
Apps | 72 | 42
Total in-scope applications
114
Already cloud-enabled
42 (37%)
Not yet cloud-enabled
72 (63%)
Total FTE-equiv. effort
1273
FTE-equiv. — cloud apps
942 (74%)
FTE-equiv. — non-cloud apps
332 (26%)
PaaS is already the dominant migration pattern (27 of 42 cloud apps) — recommend PaaS-first as the default disposition going forward.
MLJ Cloud Transformation Opportunity Assessment
5

## Slide 6
CURRENT STATE
Cloud Adoption by Business Domain
Sales/distribution-facing domains are already largely cloud; back-office and document-processing domains remain mostly on-premises.
Chart: 
| Corporate | Storage and Preservation | New Contract | Marketing/Direct Business | Customer Care / Call Center | Claims & Benefits Payment | Sales / Insurance Recruitment | Common Service Platform | Data Infrastructure | Fee Management
Non-Cloud | 25 | 13 | 10 | 7 | 5 | 4 | 4 | 3 | 1 | 0
Cloud | 8 | 2 | 2 | 2 | 3 | 2 | 9 | 7 | 2 | 5
MLJ Cloud Transformation Opportunity Assessment
6

## Slide 7
CURRENT STATE
Non-Cloud Technology Stack
The 72 in-scope non-cloud applications break down by primary language as follows. Java and VB.NET dominate; only 2 apps retain a mainframe footprint (both small Corporate Related utilities).
Chart: App Count by Stack
| Java | VB/VB.NET | Other | Mainframe (COBOL/Asm/JCL) | PL/SQL
Applications | 38 | 20 | 10 | 2 | 2
Chart: FTE-Equiv Effort by Stack
| Java | VB/VB.NET | Other | Mainframe (COBOL/Asm/JCL) | PL/SQL
FTE-Equiv Effort | 184 | 89.2 | 44.9 | 8.2 | 5.4
MLJ Cloud Transformation Opportunity Assessment
7

## Slide 8
CURRENT STATE
Application Ownership Profile
Chart: All 114 In-Scope Applications
| MetLife-Owned | Non-MetLife / COTS
In-Scope Apps | 96 | 18
Ownership × Cloud Status
Non-Cloud
Cloud
Total
MetLife-Owned
63
33
96
Non-MetLife / COTS
9
9
18
Total
72
42
114
Non-MetLife/COTS applications need a different transformation lever than rehost/replatform/refactor — a SaaS or cloud-edition negotiation with the vendor. The excluded mainframe estate (28 apps) is 100% MetLife-owned code.
MLJ Cloud Transformation Opportunity Assessment
8

## Slide 9
TRANSFORMATION CLUSTERS
Six Priority Opportunities
The 72 in-scope non-cloud applications group into six clusters, each with a recommended 6-Rs disposition.
A
K2 Workflow Management Platform
1 apps • 62.6 FTE • 1 critical
REPLACE
Target architecture already names Power Automate as successor
B
Storage & Preservation / Document Mgmt
12 apps • 44.7 FTE • 3 critical
REPLATFORM (PAAS/SAAS)
6 of 12 apps are COTS — blended replatform + SaaS approach
C
Insurance Claims & Benefits Payment
4 apps • 61.1 FTE • 3 critical
REFACTOR (AZURE PAAS)
Highest effort concentration per app; 3 of 4 critical
D
New Contract Related
10 apps • 40.4 FTE • 1 critical
REHOST / REPLATFORM
Low criticality — good early quick-win wave
E
Corporate Related Long Tail
25 apps • 40.3 FTE • 5 critical
RATIONALIZE, THEN REHOST
Includes 2 residual mainframe utilities (A04MMP, A06TOG)
F
Remaining Small Non-Cloud Apps
20 apps • 82.6 FTE • 0 critical
REHOST / REPLATFORM
Stragglers in domains that are otherwise already cloud
MLJ Cloud Transformation Opportunity Assessment
9

## Slide 10
CLUSTER SPOTLIGHT
Cluster A & Cluster B
A
K2 Workflow Management Platform
1
Apps
62.6
FTE-Equiv
1
Critical
RECOMMENDED: REPLACE
Target architecture already names Power Automate as successor
Top applications by effort:
K2
Critical
62.6
B
Storage & Preservation / Document Mgmt
12
Apps
44.7
FTE-Equiv
3
Critical
RECOMMENDED: REPLATFORM (PAAS/SAAS)
6 of 12 apps are COTS — blended replatform + SaaS approach
Top applications by effort:
W13WEP-JPN
Critical
10.0
POS-IMS
—
9.9
JP-RPASS
—
9.7
MLJ Cloud Transformation Opportunity Assessment
10

## Slide 11
CLUSTER SPOTLIGHT
Cluster C & Cluster D
C
Insurance Claims & Benefits Payment
4
Apps
61.1
FTE-Equiv
3
Critical
RECOMMENDED: REFACTOR (AZURE PAAS)
Highest effort concentration per app; 3 of 4 critical
Top applications by effort:
C12WNC-JPN
Critical
35.0
W05AMS-JPN
Critical
22.0
MDRS
Critical
2.1
D
New Contract Related
10
Apps
40.4
FTE-Equiv
1
Critical
RECOMMENDED: REHOST / REPLATFORM
Low criticality — good early quick-win wave
Top applications by effort:
NBAPPS-JPN
—
12.8
C04NWC-JPN
—
8.8
W04RRE-JPN
Critical
6.3
MLJ Cloud Transformation Opportunity Assessment
11

## Slide 12
CLUSTER SPOTLIGHT
Cluster E & Cluster F
E
Corporate Related Long Tail
25
Apps
40.3
FTE-Equiv
5
Critical
RECOMMENDED: RATIONALIZE, THEN REHOST
Includes 2 residual mainframe utilities (A04MMP, A06TOG)
Top applications by effort:
WGLWLF-JPN
—
7.2
A06TOG-JPN
Critical
5.8
Corporate Batch
—
3.7
F
Remaining Small Non-Cloud Apps
20
Apps
82.6
FTE-Equiv
0
Critical
RECOMMENDED: REHOST / REPLATFORM
Stragglers in domains that are otherwise already cloud
Top applications by effort:
WPSYEC-JPN
—
19.1
P02BKE-JPN
—
15.3
CMESB-JPN
—
12.7
MLJ Cloud Transformation Opportunity Assessment
12

## Slide 13
SEQUENCING
Recommended Transformation Roadmap
WAVE 1
Low-risk quick wins
Clusters: D, F
Low criticality, moderate effort; builds delivery momentum and validates the Azure landing zone / migration factory.
WAVE 1 (parallel)
Rationalization
Clusters: E
Retire/consolidate long-tail apps before migrating survivors; low cost, fast payback.
WAVE 2
Platform replacement + ECM replatform
Clusters: A, B
K2 → Power Automate and document management modernization; target platforms already defined.
WAVE 3
Claims & benefits refactor
Clusters: C
High effort concentration in few critical apps; needs dedicated regression/cutover planning.
MLJ Cloud Transformation Opportunity Assessment
13

## Slide 14
RFP SCOPE
Capabilities the RFP Should Require
1
Azure PaaS Migration Factory
Java/Spring Boot and .NET modernization at volume (Clusters B–F).
2
Low-Code Workflow Re-platforming
Proven experience migrating K2 (or comparable) logic to Power Automate (Cluster A).
3
Azure Landing Zone & DevOps
Familiarity with Azure DevOps / GitHub Enterprise and the target Azure IaaS/PaaS + SaaS hosting model.
4
Japan Regulatory & Language
Insurance-sector compliance experience and Japanese-language delivery capability.
5
COTS / Vendor Management
Capability to negotiate cloud/SaaS editions for the 9 non-MetLife-owned non-cloud applications.
6
Light-Touch Mainframe Support
Limited COBOL/Assembler support for 2 residual utilities in Cluster E.
MLJ Cloud Transformation Opportunity Assessment
14

## Slide 15
RISK
Risk Considerations
!
Scope Boundary
Confirm dependencies between the excluded mainframe estate and in-scope clusters (e.g., K2 or claims apps integrating with LifeComm back-end processing) during technical discovery.
!
Criticality Concentration
13 of 72 in-scope non-cloud apps (18%) are critical, concentrated in Cluster C (Claims) and Cluster A (K2). Plan rollback and regression testing accordingly.
!
Residual Mainframe Skill Need
2 small legacy-mainframe utilities remain in Cluster E — confirm the vendor can resource scarce COBOL/Assembler skills at this small scale.
!
COTS Dependency
9 non-cloud apps are non-MetLife-owned; their timeline is bounded by third-party vendor roadmaps, not MLJ's delivery capacity.
!
External Exposure
Only 1 non-cloud app is internet-facing — low near-term attack-surface risk, but exposure should not increase before target security controls are in place.
!
Data Proxy Caveat
FTE-equivalent figures are a sizing proxy from current-state resourcing fields, not migration cost estimates — supplement with technical discovery for RFP-grade costing.
MLJ Cloud Transformation Opportunity Assessment
15

## Slide 16
Next Steps
1
Validate cluster boundaries and dependencies with application owners, especially around the excluded mainframe estate.
2
Issue RFP scoped to the six in-scope clusters, sequenced per the Wave 1–3 roadmap.
3
Prioritize vendor evaluation criteria around the 13 critical applications and COTS negotiation capability.
MLJ Cloud Transformation Opportunity Assessment
16